## Cover
TEST PLAN
Project Name | CellphoneS Test |  |  | Reviewer | Lê Thị Hạnh Duyên
Project Code | CPS |  |  | Review date | 2024-10-26
Creator | Lê Thị Hạnh Duyên |  |  | Approver | Lê Thị Hạnh Duyên
Version | v1.0 |  |  | Approval Date | 2004-11-01
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2019-12-31 | v1.0 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
CPS_ProductDetail_v1 |  |  |  | 1

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
1
2
Test case design policy
Description of policies of test case design.
| # | Items | Note
1
2
Quality metric
Description of target
| # | Items | Target | Note
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) |  | Carry out test cases with highest priority first, then increase gradually.
| 2 | Test successful coverage >= 80%
| 3 | Software is correct with SRS
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing
| 2 | A specific holiday shuts down both development and testing (Tet Holiday)
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing
| 4 | If we got more pending requests with the development team
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan |  |  | Leader / Testers
2 | Create test design |  |  | Tester
3 | Create test cases |  |  | Tester
4 | Create test data |  |  | Teseter
5 | Execute system test |  |  | Teseter
6 | Defects list |  |  | Teseter
7 | Create test report |  |  | Leader / Testers
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2024-10-26 | Tester | Test manager, Team | This document itself
2 | Test cases | 2024-10-27 | Tester | Test manager, Team
3 | Defect logs | 2024-10-28 | Tester | Test manager, Team
4 | Test report | 2024-11-01 | Test leader | Test manager, Team
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1
2
3
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
Assumption
Listing of all assumption of test process.
# | Type | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1
2
3

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of the CPS system described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first) |  | CPS_ProductDetail_v1
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Smartphone |  |  |  | Standard Fsoft
OS | Window 10 64bit Android 6.0 or higher
Software | Edge 44.18362.329.0
Database | MS SQL
Browser | Edge 44.18362.329.0
Network configured | LAN Wifi

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | Lê Thị Hạnh Duyên | Leader | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the product information display function.
2 | Lê Thị Hạnh Duyên | Member | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the product review feature.
3 | Lê Thị Hạnh Duyên | Member | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the add to cart function.
4 | Lê Thị Hạnh Duyên | Member | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the product sharing feature.
5 | Lê Thị Hạnh Duyên | Member | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the promotional information feature.
6 | Lê Thị Hạnh Duyên | Member | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the warranty information feature.
7 | Lê Thị Hạnh Duyên | Member | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the product comparison feature.
8 | Lê Thị Hạnh Duyên | Member | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the large image loading feature.
9 | Lê Thị Hạnh Duyên | Member | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the related products search feature.
10 | Lê Thị Hạnh Duyên | Member | - Read and analyze documentation, design test cases, write test cases, execute test cases, and log bugs for the manufacturer information feature.
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2024-10-26 | 2024-10-27
2 | Create test design | 2024-10-27 | 2024-10-28
3 | Create test case | 2024-10-26 | 2024-10-28
4 | Execute test and log bugs | 2024-10-28 | 2024-10-30
5 | Evaluting exit criteria & Test report | 2024-10-30 | 2024-10-31
6 | Review | 2024-10-31 | 2024-11-01
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 1
| Create test design | 0 | 1
| Create test case | -2 | 2
| Execute test and log bugs | -1 | 2
| Evaluting exit criteria & Test report | 0 | 1
| Review | 0 | 2
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | December
|  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Create test plan | Team | bar: December 9
2 | Create test design | Lê Thị Hạnh Duyên | bar: December 14
2024-01-02 | Hiển thị thông tin sản phẩm | Lê Thị Hạnh Duyên | bar: December 14
2024-02-02 | Kiểm tra tính năng đánh giá sản phẩm | Lê Thị Hạnh Duyên | bar: December 14
2024-03-02 | Kiểm tra tính năng thêm vào giỏ hàng | Lê Thị Hạnh Duyên | bar: December 14
2024-04-02 | Kiểm tra tính năng chia sẻ sản phẩm | Lê Thị Hạnh Duyên | bar: December 14
2024-05-02 | Kiểm tra thông tin khuyến mãi (nếu có) | Lê Thị Hạnh Duyên | bar: December 14
2024-06-02 | Kiểm tra thông tin bảo hành và hỗ trợ | Lê Thị Hạnh Duyên | bar: December 14
2024-07-02 | Kiểm tra tính năng so sánh sản phẩm | Lê Thị Hạnh Duyên | bar: December 14
2024-08-02 | Kiểm tra khả năng tải hình ảnh sản phẩm lớn | Lê Thị Hạnh Duyên | bar: December 15
2024-09-02 | Kiểm tra tính năng tìm kiếm sản phẩm liên quan | Lê Thị Hạnh Duyên | bar: December 16
2024-10-02 | Kiểm tra thông tin nhà sản xuất và nguồn gốc sản phẩm | Lê Thị Hạnh Duyên | bar: December 16 to December 18
2024-11-02 | Review | Lê Thị Hạnh Duyên | bar: December 16 to December 18
3 | Create test case | Lê Thị Hạnh Duyên | bar: December 16 to December 18
2024-01-03 | Hiển thị thông tin sản phẩm: Đảm bảo rằng tên, mô tả, giá cả, và hình ảnh sản phẩm hiển thị chính xác | Lê Thị Hạnh Duyên | bar: December 16 to December 18
2024-02-03 | Tính năng đánh giá sản phẩm: Đảm bảo người dùng có thể gửi và xem đánh giá cho sản phẩm | Lê Thị Hạnh Duyên | bar: December 16 to December 18
2024-03-03 | Thêm vào giỏ hàng: Đảm bảo người dùng có thể thêm sản phẩm vào giỏ hàng thành công | Lê Thị Hạnh Duyên | bar: December 16 to December 18
2024-04-03 | Chia sẻ sản phẩm: Đảm bảo người dùng có thể chia sẻ thông tin sản phẩm qua mạng xã hội | Lê Thị Hạnh Duyên | bar: December 16 to December 18
2024-05-03 | Thông tin khuyến mãi: Đảm bảo thông tin khuyến mãi hiển thị đúng và rõ ràng | Lê Thị Hạnh Duyên | bar: December 16 to December 18
2024-06-03 | Thông tin bảo hành: Đảm bảo thông tin về bảo hành và hỗ trợ khách hàng hiển thị đầy đủ | Lê Thị Hạnh Duyên | bar: December 16 to December 18
2024-07-03 | So sánh sản phẩm: Đảm bảo người dùng có thể so sánh nhiều sản phẩm cùng lúc | Lê Thị Hạnh Duyên | bar: December 16 to December 18
2024-08-03 | Tải hình ảnh lớn: Đảm bảo hình ảnh sản phẩm lớn tải nhanh và rõ nét | Lê Thị Hạnh Duyên | bar: December 19
2024-09-03 | Tìm kiếm sản phẩm liên quan: Đảm bảo hệ thống gợi ý các sản phẩm liên quan chính xác | Lê Thị Hạnh Duyên | bar: December 20 to December 27
2024-10-03 | Thông tin nhà sản xuất: Đảm bảo thông tin về nhà sản xuất và nguồn gốc hiển thị đầy đủ và chính xác | Lê Thị Hạnh Duyên | bar: December 20 to December 26
2024-11-03 | Review: Đánh giá tổng quát về trải nghiệm người dùng trên trang chi tiết sản phẩm | Lê Thị Hạnh Duyên | bar: December 20 to December 26
4 | Execute test and logs bug | Lê Thị Hạnh Duyên | bar: December 20 to December 26
2024-01-04 | Hiển thị thông tin sản phẩm: Ghi lại bất kỳ lỗi nào khi hiển thị thông tin | Lê Thị Hạnh Duyên | bar: December 20 to December 26
2024-02-04 | Tính năng đánh giá sản phẩm: Ghi lại lỗi khi gửi hoặc xem đánh giá | Lê Thị Hạnh Duyên | bar: December 20 to December 26
2024-03-04 | Thêm vào giỏ hàng: Ghi lại lỗi khi thêm vào giỏ hàng không thành công | Lê Thị Hạnh Duyên | bar: December 20 to December 26
2024-04-04 | Chia sẻ sản phẩm: Ghi lại lỗi trong quá trình chia sẻ thông tin | Lê Thị Hạnh Duyên | bar: December 20 to December 26
2024-05-04 | Thông tin khuyến mãi: Ghi lại lỗi nếu thông tin khuyến mãi không hiển thị đúng | Lê Thị Hạnh Duyên | bar: December 20 to December 26
2024-06-04 | Thông tin bảo hành: Ghi lại lỗi nếu thông tin không đầy đủ hoặc sai lệch | Lê Thị Hạnh Duyên | bar: December 20 to December 26
2024-07-04 | So sánh sản phẩm: Ghi lại bất kỳ vấn đề nào khi so sánh các sản phẩm | Lê Thị Hạnh Duyên | bar: December 20 to December 26
2024-08-04 | Tải hình ảnh lớn: Ghi lại lỗi nếu hình ảnh không tải được hoặc tải chậm | Lê Thị Hạnh Duyên | bar: December 27
2024-09-04 | Tìm kiếm sản phẩm liên quan: Ghi lại lỗi nếu không tìm thấy các sản phẩm liên quan đúng cách | Lê Thị Hạnh Duyên | bar: December 28
2024-10-04 | Thông tin nhà sản xuất: Ghi lại lỗi nếu thông tin không chính xác hoặc thiếu sót | Lê Thị Hạnh Duyên | bar: December 31
2024-11-04 | Review: Ghi lại tổng kết về trải nghiệm kiểm thử | Lê Thị Hạnh Duyên
5. Evaluating exit criteria & Test report | Tổng hợp báo cáo kiểm thử từ tất cả các trường hợp kiểm thử
6. Review | Xem xét báo cáo kiểm thử và đưa ra nhận xét từ Team

## Appendix
Appendix
Term definition
# | Term | Definition/Explanation
1 | Product Information | Details about a product, including name, description, specifications, and price.
2 | Product Review | User-generated feedback and ratings about a product's quality and performance.
3 | Add to Cart | A feature that allows users to select a product and place it in their shopping cart.
4 | Product Sharing | The ability for users to share product information via social media or other platforms.
5 | Promotional Information | Details regarding discounts, special offers, or sales related to products.
6 | Warranty Information | Information about the warranty coverage for a product, including duration and terms.
7 | Product Comparison | A feature that allows users to compare multiple products based on various criteria.
8 | Large Image Loading | The capability to load high-resolution images of products for better visualization.
9 | Related Products Search | A feature that suggests similar or complementary products based on user interest.
10 | Manufacturer Information | Details about the company that produces the product, including background and contact info.
11 | Related Products Search | A feature that suggests similar or complementary products based on user interest.
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14
Members
1 | Lê Thị Hạnh Duyên
2 | Lê Thị Hạnh Duyên
3 | Lê Thị Hạnh Duyên